Proud:

- Contact Center: CCAS team signed Time & Materials contract and aligning on AB testing methodology for CrestaAI AB pilot, plus developing 4 new service flows for RCI/CEL. For Lead Prioritization, DS + IT Teams actively working towards pushing prioritized CTI leads into Siebel for CEL and identifying next steps for BK2CX leads.

- Loyalty Pilot & CLTV: For the "Spend-2-Save" Pilot, DS team delivered a refined view of success and break-even, accounting for both incremental onboard and pcp spend as well as ticket revenue from increased booking demand. Actively working on "Taste of Tier" pilot and refining target population segments to better understand behavior of our high-value, infrequent guests. For CLTV, collaborating with related business units (Data Engineering, Revenue Planning, and Corporate Planning) to create a high-level roadmap to move from POC to enterprise level resource.

- Revenue Management (RCI + CEL): Held our first Tri-Branded RM Steering Call with constructive discussion on 2025 Priorities and comparison of automation capabilities between RCI/CEL. For CEL, FIT GTY-Berthing Automation went live this week and >4.7k bookings were successfully berthed, significantly reducing the backlog of manual berthings. For RCI, delivered SPI-guided deployment tracks for 2026-2027 sailings, which represents the team's first step towards revenue-optimizing track targets using SPI. DS/MLOPs Teams actively working on Q2 deliveries for Pricing Elasticity Enhancements & Category Gapping Optimization (GTY-lead), as well as PRE Code Refactoring, Overselling Modeling, and ADA Compliance Automation.

- Supply Chain: DS Team extended Silversea (HF&B) demand forecasts into 2026 enabling improved long‐term planning, and delivered new HF&B reporting data unifying Silversea spend data and historical & forecasted consumption, which is a key step towards developing a Silversea finance reporting tool (like RCI & CEL enjoy).

Excited:

- E-Commerce: Implemented a new uplift marketing model, which help our E-Commerce teams better understand which customer's booking propensity will be enhanced through marketing campaigns. Continuing to enhance the Databricks Genie app that is helping our E-Commerce teams more easily identify high-value customers.

- Global Marine Operations: Completed tag mapping and Service/Hotel/Machinery/HVAC dynamic model development for Icon of the Seas. Met with Energy Management leadership to align on MIAP roles & responsibilities, specifically future tag-mapping and OPC server installations. Had a meeting with Voyage Data Recorder (i.e. our ship's black boxes) manufacturer Danelec along with Maritime Safety teams to expand MIAP program into Maritime Safety. Enhanced performance monitoring models on 8 additional ships and actively pursuing additional enhancements to our Dynamic Modeling framework.

- Medallia Generative AI "Text Summarization" Pilot: Delivered ad-hoc request from CEL to create recurring reporting around beverage package pricing. Developed new version of Medallia-Chat, which users can ask questions to Medallia directly and working to extract extract insights from Qualtrics survey feedback related to "Favorite Customer Activities". Actively aligning with different teams on priorities (i.e. RCI/CEL Hotel Ops, Marketing, and Consumer Insights teams) and will be holding a STEERING call to develop a consolidated work pipeline between interested departments

- PCP Pricing Automation: Refining analysis for AB Testing of Perfect Day Cabanas Productions and completed initial EDA on important factors that affect demand for Beverage Packages.

- PCP Product Recommendations: Developed 3 additional apriori recommender models (i.e. Customers-Also-Viewed, Customers-Also-Addtocart, Customers-Also-Purchased).